## QA Test
# | Features | Scenario ID | Test Scenario | Location | Test cases ID | Test Cases | Expected Bahavior | Result |  |  | Test Date | Notes | Trello #
[8 empty] | Chrome | Safari | Firefox
0 | Project setup
1 | Login | 1.1 | Login onboarding screen
|  | 1.2 | Login dengan Google
|  | 1.3 | Login dengan Facebook
|  | 1.4 | Login dengan Linkedin | [9 empty] | [56]
2 | Individual Account Registration | 2.1 | Register with Google | [9 empty] | [146]
|  | 2.2 | Register with Facebook
|  | 2.3 | Register with Linkedin | [9 empty] | [56]
|  | 2.4 | Register with Email
|  | 2.5 | Reset password
|  | 2.6 | Forgot Password
|  | 2.7 | Notifications
3 | Homepage - Main | 3.1 | Homepage
|  | 3.2 | Header & Footer
4 | Homepage - Search | 4.1 | Search Result Page - 0 Result
|  | 4.2 | Search Result Page - Card View
|  | 4.3 | Search Result Page - Map View
|  | 4.4 | Search Result Page - More Filter
5 | Property Listing | 5.1 | Listing Detail - Main
|  | 5.2 | Listing Detail - Negotiation
|  | 5.3 | Listing Detail - Onsite Schedule Tour
|  | 5.4 | Listing Detail - Virtual Schedule Tour
6 | Payment Page | 6.1 | Payment Page
|  | 6.2 | Prepayment - Rent Detail
|  | 6.3 | Prepayment - Review Rules
|  | 6.4 | Prepayment - Confirm Profile
|  | 6.5 | Prepayment - Installment Detail
|  | 6.6 | Prepayment - Digital Contract
|  | 6.7 | Prepayment - Installment
7 | User Dashboard | 7.1 | User Profile - Edit Profile
|  | 7.2 | User Profile - Digital Identity
|  | 7.3 | User Profile - Legal Document
|  | 7.4 | User Profile - Account Setting
|  | 7.5 | Dashboard - Main
|  | 7.6 | Dashboard - My Rent
|  | 7.7 | Dashboard - My Ongoing Activities
|  | 7.8 | Dashboard - My Rent Hsitory
|  | 7.9 | Dashboard - My Rent History Property Card
|  | 7.10 | Save Property to Favorite
|  | 7.11 | Dashboard - Favorite
|  | 7.12 | Dashboard - Notification
|  | 7.13 | Dashboard - Notification List
8 | Listing | 8.1 | Create New Listing - Basic Property Information
|  | 8.2 | Create New Listing - Tell Us The Details
|  | 8.3 | Create New Listing - Payment Preference
|  | 8.4 | Create New Listing - Review Submit
|  | 8.5 | Create New Listing - Basic Property Information
|  | 8.6 | My Listing - Listed
|  | 8.7 | My Listing - Listed - Contract
|  | 8.8 | My Listing - Property Detail
|  | 8.9 | My Listing - Property Detail - Review Page
|  | 8.10 | My Listing - Drafted
|  | 8.11 | My Listing - Pending
|  | 8.12 | Listing Approval Process
9 | Multi Languages | 9.1 | Multi Language - Homepage
|  | 9.2 | Multi Language - Detail Page
|  | 9.3 | Multi Language - Search Page
|  | 9.4 | Multi Language - Dashboard Profile
|  | 9.5 | Multi Language - Dashboard My Rent
|  | 9.6 | Multi Language - Add Property

## contoh
# | Features | Scenario ID | Test Scenario | Location | Test cases ID | Test Cases | Expected Bahavior | Result |  |  | Test Date | Notes | Trello #
[8 empty] | Chrome | Safari | Firefox
0 | Project setup
1 | Login | 1.1 | Login onboarding screen | Sign in | 1.1.1 | Pastikan font greeting sesuai dengan mockup | Invision | Passed | Passed | Passed | 2019-07-02 01:13
[5 empty] | 1.1.2 | Pastikan adanya error message jika salah format email, dan styling sesuai dengan dokumen | Web Browser | Passed | Passed | Passed | 2019-07-02 02:27
[5 empty] | 1.1.3 | Pastikan adanya error message jika salah memasukan password atau email, dan styling sesuai dengan dokumen | Web Browser | Passed | Passed | Passed | 2019-07-02 03:27
[5 empty] | 1.1.4 | Pastikan fungsi "keep me signed in" berfungsi, dan styling sesuai dengan dokumen | Web Browser | Passed | Passed | Passed | 2019-07-02 03:28
[5 empty] | 1.1.5 | Pastikan fungsi "forgot password" berfungsi, dan styling sesuai dengan dokumen | Invision | Failed | Failed | Failed | 2019-07-02 03:47
|  | 1.2 | Login dengan Google | Sign in | 1.1.2 | Style telah sesuai dan API telah berjalan |  | Passed | Passed | Passed | 2019-07-05 01:30
|  | 1.3 | Login dengan Facebook | Sign in | 1.1.3 | Style telah sesuai dan API telah berjalan |  | Passed | Passed | Passed | 2019-07-05 02:03
|  | 1.4 | Login dengan Linkedin | Sign in | 1.1.4 | Style telah sesuai dan API telah berjalan |  | Failed | Failed | Failed | 2019-07-05 02:33 | API error | [56]
2 | Individual Account Registration | 2.1 | Register with Google | Sign up | 2.1.1 | Style telah sesuai dan API telah berjalan |  | Failed | Failed | Failed | 2019-07-05 03:09 | API error | [146]
|  | 2.2 | Register with Facebook | Sign up | 2.2.1 | Style telah sesuai dan API telah berjalan |  | Failed | Failed | Failed | 2019-07-05 03:12 | Sign up API redirected to login API instead
|  | 2.3 | Register with Linkedin | Sign up | 2.3.1 | Style telah sesuai dan API telah berjalan |  | Failed | Failed | Failed | 2019-07-05 03:13 | API error | [56]
|  | 2.4 | Register with Email | Sign up | 2.4.1 | Style dan wording form telah sesuai |  | Passed | Passed | Passed | 2019-07-05 03:19
[5 empty] | 2.4.2 | Tampilan pesan error di mandatory field yg kosong dan tak bisa continue |  | Passed | Passed | Passed | 2019-07-05 03:22
[5 empty] | 2.4.3 | Pengecekan format email dan nomor telepon berjalan |  | Passed | Passed | Passed | 2019-07-05 03:24
[5 empty] | 2.4.4 | Mendaftar ulang memakai email yang telah terdaftar akan menampilkan pesan error dan tak bisa continue |  | Passed | Passed | Passed | 2019-07-05 03:26
[5 empty] | 2.4.5 | Memasukkan format nomor telepon salah (eg: 081abc) akan menampilkan pesan error dan tak bisa continue |  | Failed | Failed | Failed | 2019-07-05 03:29 | Nomor telepon angka+nomor tetap bisa continue
[5 empty] | 2.4.6 | Modal "Email sent" ada dan style/wording telah sesuai |  | Passed | Passed | Passed | 2019-07-05 03:33
[5 empty] | 2.4.7 | Modal "Email sent" ada dan user tetap di halaman sebelumnya |  | Failed | Failed | Failed | 2019-07-05 03:36 | Gambar modal tidak muncul. File not found
|  | 2.5 | Reset password |  | 2.5.1 | Change password interface telah sesuai |  | Passed | Passed | Passed | 2019-07-08 03:05
[5 empty] | 2.5.2 | Script penggantian password berjalan dan password terganti |  | Failed | Failed | Failed | 2019-07-08 03:06 | Token invalid error | [150]
[5 empty] | 2.5.3 | Styling telah sesuai dengan mockup |  | Passed | Passed | Passed | 2019-07-07
|  | 2.6 | Forgot Password |  | 2.6.1 | Forgot password via registered phone | Invision | Failed | Failed | Failed | 2019-07-02 03:57 | Nomor sudah benar namun muncul pesan error incorrect phone number. Send me a link mestinya Send me the link
[5 empty] | 2.6.2 | Forgot password via registered email | Invision | Passed | Passed | Passed | 2019-07-02 04:13 | Email reset password tidak muncul di inbox
|  | 2.7 | Notifications |  | 2.7.1 | ?
3 | Homepage - Main | 3.1 | Homepage |  | 3.1.1 | Font sesuai dengan mockup |  | Passed | Passed | Passed | 2019-07-07
[5 empty] | 3.1.2 | Seluruh hyperlink telah terisi |  | Failed | Failed | Failed | 2019-07-07 | See more - property recommendation, commute features, 360 view, live virtual view, discover listings
[5 empty] | 3.1.3 | Style, background & pattern telah sesuai dengan mockup |  | Passed | Passed | Passed | 2019-07-07
[5 empty] | 3.1.4 | Wording dan capital telah sesuai dan tanpa typo |  | Failed | Failed | Failed | 2019-07-08 | Main heading "Need and upgrade" should be "Need an upgrade" | [142]
|  | 3.2 | Header & Footer | Footer | 3.2.1 | Style footer telah sesuai dengan mockup |  | Passed | Passed | Passed | 2019-07-08
|  |  |  | Footer | 3.2.2 | Style dan wording form "Share it here" telah sesuai |  | Passed | Passed | Passed | 2019-07-08
|  |  |  | Footer | 3.2.3 | Terdapat form Thank you setelah menginput Share it here |  | Failed | Failed | Failed | 2019-07-08 | Tidak ada form thank you | [149]
|  |  |  | Footer | 3.2.4 | Seluruh hyperlink telah terisi |  | Failed | Failed | Failed | 2019-07-08 | Link Services, Company & FYI belum ada satupun
|  |  |  | Footer | 3.2.5 | Opsi Subscribe telah berjalan dengan baik |  | Failed | Failed | Failed | 2019-07-08
|  |  |  | Header | 3.2.6 | Logo dan Tulisan SEWAGI telah sesuai dengan mockup |  | Passed | Passed | Passed | 2019-07-08
|  |  |  | Header | 3.2.7 | Flex-Navbar telah berjalan dengan baik |  | Passed | Passed | Passed | 2019-07-08
|  |  |  | Header | 3.2.8 | Search box dan geolocation berjalan dengan baik |  | Passed | Passed | Passed | 2019-07-08
|  |  |  | Header | 3.2.9 | Seluruh hyperlink telah terisi |  | Passed | Passed | Passed | 2019-07-08
|  |  |  | Header | 3.2.10 | Smooth scrolling tombol About berjalan dgn baik |  | Failed | Failed | Failed | 2019-07-08 | Smooth scrolling tidak berjalan
4 | Homepage - Search | 4.1 | Search Result Page - 0 Result |  | 4.1.1 | Style, background & pattern telah sesuai dengan mockup |  | Passed | Passed | Passed | 2019-07-08
[5 empty] | 4.1.2 | Seluruh hyperlink telah terisi |  | Failed | Failed | Failed | 2019-07-08 | Tombol Share it here dan Discover Listing belum berfungsi
[5 empty] | 4.1.3 | Default page load Living Condition both enabled |  | Passed | Passed | Passed | 2019-07-09 | Living Condition set but not updated into nav bar
[5 empty] | 4.1.4 | Default page load : "At this time we only serve the city of Jakarta" |  | Failed | Failed | Failed | 2019-07-09 | Missing text
[5 empty] | 4.1.5 | Default page load : "Jakarta" hyperlink to Location = Jakarta, Indonesia |  | Failed | Failed | Failed | 2019-07-09 | Not exist text
[5 empty] | 4.1.6 | Default page load : Sort by = Latest |  | Failed | Failed | Failed | 2019-07-09 | Current Default = Most viewed
[5 empty] | 4.1.7 | Fungsi MAP telah berjalan sesuai chart |  | Failed | Failed | Failed | 2019-07-10 | Fungsi map masih dalam proses dev
|  | 4.2 | Search Result Page - Card View |  | 4.2.1 | Style, background & pattern telah sesuai dengan mockup |  | Passed | Passed | Passed | 2019-07-10
[5 empty] | 4.2.2 | Default page load Living Condition both enabled |  | Passed | Passed | Passed | 2019-07-10
[5 empty] | 4.2.3 | Default page load : Sort by = Latest |  | Failed | Failed | Failed | 2019-07-10 | Current Default = Most viewed
[5 empty] | 4.2.4 | Seluruh filter berjalan dengan baik |  | Passed | Passed | Passed | 2019-07-10
[5 empty] | 4.2.5 | Seluruh hyperlink telah terisi |  | Failed | Failed | Failed | 2019-07-10 | Tombol Share it here dan Discover Listing belum berfungsi
[5 empty] | 4.2.6 | Fungsi MAP telah berjalan sesuai chart |  | Failed | Failed | Failed | 2019-07-10 | Fungsi map masih dalam proses dev
|  | 4.3 | Search Result Page - Map View
|  | 4.4 | Search Result Page - More Filter
5 | Property Listing | 5.1 | Listing Detail - Main
|  | 5.2 | Listing Detail - Negotiation
|  | 5.3 | Listing Detail - Onsite Schedule Tour
|  | 5.4 | Listing Detail - Virtual Schedule Tour
6 | Payment Page | 6.1 | Payment Page
|  | 6.2 | Prepayment - Rent Detail
|  | 6.3 | Prepayment - Review Rules
|  | 6.4 | Prepayment - Confirm Profile
|  | 6.5 | Prepayment - Installment Detail
|  | 6.6 | Prepayment - Digital Contract
|  | 6.7 | Prepayment - Installment
7 | User Dashboard | 7.1 | User Profile - Edit Profile
|  | 7.2 | User Profile - Digital Identity
|  | 7.3 | User Profile - Legal Document
|  | 7.4 | User Profile - Account Setting
|  | 7.5 | Dashboard - Main
|  | 7.6 | Dashboard - My Rent
|  | 7.7 | Dashboard - My Ongoing Activities
|  | 7.8 | Dashboard - My Rent Hsitory
|  | 7.9 | Dashboard - My Rent History Property Card
|  | 7.10 | Save Property to Favorite
|  | 7.11 | Dashboard - Favorite
|  | 7.12 | Dashboard - Notification
|  | 7.13 | Dashboard - Notification List
8 | Listing | 8.1 | Create New Listing - Basic Property Information
|  | 8.2 | Create New Listing - Tell Us The Details
|  | 8.3 | Create New Listing - Payment Preference
|  | 8.4 | Create New Listing - Review Submit
|  | 8.5 | Create New Listing - Basic Property Information
|  | 8.6 | My Listing - Listed
|  | 8.7 | My Listing - Listed - Contract
|  | 8.8 | My Listing - Property Detail
|  | 8.9 | My Listing - Property Detail - Review Page
|  | 8.10 | My Listing - Drafted
|  | 8.11 | My Listing - Pending
|  | 8.12 | Listing Approval Process
9 | Multi Languages | 9.1 | Multi Language - Homepage
|  | 9.2 | Multi Language - Detail Page
|  | 9.3 | Multi Language - Search Page
|  | 9.4 | Multi Language - Dashboard Profile
|  | 9.5 | Multi Language - Dashboard My Rent
|  | 9.6 | Multi Language - Add Property

## old2 (hidden)
Passed
Failed